## Sheet1
MediaChips
Task Name |  |  | Duration
| Analysis & design |  | 23 | days
|  | Design Site Map | 3 | days
|  | Design Site for interfice | 5 | days
|  | Workflow: Update content & Master Data | 4 | days
|  | Workflow: File Sharing - inbond & outbond | 4 | days
|  | Report : View page report, File server report | 5 | days
|  | Finalizing FSD Document | 2 | days
| Development |  | 75 | days
|  | Design Template | 5 | days
|  | Code Controller | 30 | days
|  | Update Content | 15 | days
|  | Master Data | 15 | days
|  | View Page Report | 10 | days
| Testing |  | 4 | days
|  | SIT (System Integration test) | 2 | days
|  | UAT (User Acceptance Test) | 2 | days
| Documentation |  | 12 | days
|  | User Guide | 6 | days
|  | Admin Guide | 6 | days
| Delivery |  | 0 | days