## Sheet1
MediaChips
Task Name |  |  | Duration
| Analysis & design |  | 23 | days
|  | Design Site Map | 3 | days
|  | Design Site for interfice | 5 | days
|  | Workflow: Update content & Master Data | 4 | days
|  | Workflow: File Sharing - inbond & outbond | 4 | days
|  | Report : View page report, File server report | 5 | days
|  | Finalizing FSD Document | 2 | days
| Development |  | 75 | days
|  | Design Template | 5 | days
|  | Code Controller | 30 | days
|  | Update Content | 15 | days
|  | Master Data | 15 | days
|  | View Page Report | 10 | days
| Testing |  | 4 | days
|  | SIT (System Integration test) | 2 | days
|  | UAT (User Acceptance Test) | 2 | days
| Documentation |  | 12 | days
|  | User Guide | 6 | days
|  | Admin Guide | 6 | days
| Delivery |  | 0 | days

## Sheet2
Description |  | Qty | Monthley Cost | Cost | Subtotal
SDM |  | 6
| SA (Sistem Analis) | 1 | 15000000 |  | 15000000
| Designer | 2 | 16000000 |  | 16000000
| Developer | 3 | 33000000 |  | 33000000
support tools |  | 19
| Server HP ProLiant DL500 Series | 1 |  | 60000000 | 60000000
| Notebook (include software dev) | 8 |  | 88000000 | 88000000
| Printer HP Color LaserJet | 3 |  | 4149000 | 4149000
| Mesin Fotocopy | 2 |  | 15500000 | 15500000
| Router | 1 |  | 21400000 | 21400000
| Projector WXGA | 1 |  | 15000000 | 15000000
| CCTV Camera | 3 |  | 3600000 | 3600000
Oprasional
| Listrik |  | 10000000 |  | 10000000
| Internet Connection |  | 2035000 |  | 2035000
| Telepon |  | 8000000 |  | 8000000
Other |  |  |  | 200000000 | 200000000
|  |  |  | Total | 491684000